Mochi Tsuki 2023 Action Plan/Suggestions for next year

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **What** | **Who** | **Status** | **Details** | **Changes/suggestions for 2024** |
| Secure Burn permit | Carol | done | Submitted; waiting for approval – December |  |
| Secure Food Handling permit | Carol | After inspection | Submitted; paid $95; waiting for final approval |  |
| Secure Woodward and rooms | Debra | done | Securing 212 and 301 and teacher’s breakroom; girls locker room |  |
| Friday night set up and orientation | Carol |  | Power point presentation4-6 set up (school lets out at 3:30)6:00 – 6:30 orientation/pizza6:30 – mochi forming/obon dancing intro/allow volunteer purchases2 mikes for the gym | Need microphoneLaptop HDMI attachmentThat’s a Some pizza order for 5:30(2 large cheese, 2 large meat, 2 large vegarian gorgonzola, 2 large vegetarian) - $275 |
| Posters | Tracy | done | Request mask wearingAdd obon eventChange to 33rd annualSponsor: T and C |  |
| Secure T and C contact and supply ordering | Ron Nakata/Vern Nakata | done |  | Need mochi bags – used them all up and additional clam shell boxes |
| Secure area leaders |  |  | Trivia WheelVolunteer Check in |  |
| Secure Taiko Group-order sushi | Carol | DoneDone – 1/7 8am p/u | Planning on a noon show and 2:00 | Order large platter of sushiPay their feePay their ferry fees |
| Collecting special prizes for “gold” number on trivia wheel | Mariko Green | done | Soliciting friends for donations |  |
| Secure Obon leaders/process  | Katzumi Frogner; Bianca and Jeff Mariko Green | done | ½ hour from 1-1:30 pmOutside covered areaNeed music, speakers and microphone | Block off the covered area with cones so no one parks thereConsider adding a third dance |
| Confirm times for Friday and Saturday. |  | Done | Setup time/Date:**Friday, January 6 from 4-7 pm** – setup, rice prep, equipment and supply delivery, an rolling, orientation, dance practice(!)4-6 pm setup6-6:30 – orientation/pizza6:30 – mochi forming/obon dancing**Saturday, January 7**7am-11 am11am-3 pm – eventNoon-12:45 – taiko performance #11:00-1:30 – Obon Dance 1 and 2 2:00-2:45 – Taiko performance #23:00-4:00 - cleanup |  |
| Taiko management | Carol | done | Print and distribute 700 tickets for each show – Color coded tickets for Noon show--PINK2:00 show---BLUECollect based on where they live: Bainbridge, Kitsap, not KitsapTape floor, carpet for audience walkway only |  |
| Livestream on BIJAC facbook page | Jay Matsudaira |  | Get him access to the webpage |  |
| Columbia bank credit card readers | Debra | Done | Readers needed for merchandise sales, mochi donations, donations at the doorDebraLynnJeff O’MeareAl QuanCarol | Used 4 readers:2 3 at merchandise sales1 at mochi distributionWe could use at least 2 for mochi distribution |
| T-shirt inventory-other goods | Debra GrindelandLynne Brunelle | Done | What do we need to sell?Stan and Eileen – determine t-shirt inventory neededLynn will make her mochi dishes to sell – we receive a % of sales |  |
| Confirm with COBI | Carol | Done | -providing medical support-providing parking and traffic control – provide list of handicapped parking/access for volunteer parking in North Lot – use cones | We can use parking monitors at Woodward earlier – at 9:30-10:00, especially to guard the North gate and parking access |
| ~~Additional drinking water~~ | ~~Carol~~ | ~~Done~~ | ~~Olympic springs delivering water jugs and dispensers; picking up at event end~~ | Don’t need this |
| Handwashing stations | Debra | Done | Does the school still have those portable washing stations? | Yes – the one station caused a bottleneck – need to monitor the water levels and wet floor |
| Food handler cards |  | Requested | Kitchen and outside rice prep |  |
| Confirm with BISD:Keys to WWLights on Friday/Saturday in parking lotsVerify permits | Carol | Done | Bill Ackerman – send floor plan  | He needs the signed commissary agreement, food handler applicationParking lot lots need to be turned on by 7 am on Saturday. |
| Food for Friday night | Carol |  | Pizza delivery from That’s a some pizza;water |  |
| Create setup actions | Carol |  |  | Photos really helped |
| Create job descriptions | Carol |  |  |  |
| Set up reminder signup genius email | Carol | Done |  |  |
| Follow up email |  |  | Thank volunteers:Include news linksInclude fun stats |  |
| Supply needs for 2024 |  |  | Signs:* **Obon Dancing** (arrow left) for the Gym exit door
* No entry -please enter through the South entrance (3 for North exterior doors)
* **Doors open at 11 – 3**-4 for the North exterior doors
* Poster hanging 3M strips
* 5 more foam core boards (18x24)

OTHER ISSUES* More large origami paper – plenty of newsprint available
* Plenty of kid activity cards left – *no need to order*
* Add another set of taiko ticket collection boxes to allow the line to move faster--DONE

Need to print taiko tickets700-537 = 163 pink700-577= 123 BLUE |  |